## Sprint Report
| Cadence Report |  |  | Retrospective Presentation link
https://docs.google.com/presentation/d/1M9krlgApK5YYPWmppuCTFO0fOlU4ymhbHlkZNtcFoUA/edit?usp=sharing
Project Name: | Drone Link | Cadence# | 2
Team Name: |  | Start: | End:
TEAM MEMBERS | Alex | 2020-10-05 | 2020-10-19
Lucas
Sam
Vincent
Blake
# of story points created at beginning of cadence | # of story points added throughout cadence | Total Story Points | # of story points completed (velocity)
31 | 5 | 36 | 12
The cadences velocity is not a good representation of our velocity as we began a large amount of tickets that haven't been completed as we created and evolved tickets as we went throught this difficult cadence
| Cadence | Expected | Velocity
| 1 | 43 | 35
| 2 | 36 | 12
| Issues | %
Vincent | 2.5 | 20.83
Alex | 0 | 0
Blake | 5 | 41.67
Lucas | 0 | 0
Sam | 4.5 | 37.5
Impediments
Impediment | Reported On | Resolved On | Resolution
Retrospective
What went well in this cadence?
The outing to see the drones in person worked nicely.
Communication as a team improved, especially with the face-to-face outing.
We developed a higher understanding of what our project is going to look like.
What did not go well in this cadence?
Midterm time management for project
Blocked tasks holding back team members
What can we do differently to improve?
We can make sure that work is done more consistently and not pushed off.
Communicate possible work slowdowns prior to the start of a cadence. (Midterms, Personal)

## Calculations
Issue ID | Title | State | Author | Author Username | Assignee | Assignee Username | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate | Time Spent | Epic ID | Epic Title
1 | Research Database for project | Closed | Alex | Buddylgreen | Lucas | laroccol | No | No |  | 2020-09-14 21:31 | 2020-09-30 19:43 | 2020-09-30 19:43 |  | 3 |  | 0 | 25200
2 | Research Front End Web framework | Closed | Alex | Buddylgreen | Blake Masbruch | masbruchba | No | No |  | 2020-09-14 21:33 | 2020-10-07 23:22 | 2020-10-06 19:32 |  | 3 |  | 0 | 12600
3 | Research Back End web frameworks | Closed | Alex | Buddylgreen | Sam Forest | SamForest | No | No |  | 2020-09-14 21:34 | 2020-09-30 19:03 | 2020-09-28 22:18 |  | 5 |  | 0 | 18900
4 | Research alternatives to mqtt | Closed | Alex | Buddylgreen | Lucas | laroccol | No | No |  | 2020-09-14 21:34 | 2020-10-05 22:13 | 2020-10-05 22:13 |  | 3 |  | 0 | 18000
5 | Develop testing strategy | Closed | Alex | Buddylgreen | Alex, Vincent Krenz | Buddylgreen, krenzva | No | No |  | 2020-09-14 21:35 | 2020-10-12 21:57 | 2020-10-12 21:57 |  | 8 |  | 0 | 36300
6 | Wireframes for web application | Closed | Alex | Buddylgreen | Vincent Krenz, Sam Forest | krenzva, SamForest | No | No |  | 2020-09-14 21:36 | 2020-10-21 19:17 | 2020-10-21 19:17 |  | 5 |  | 0 | 21600
7 | Research hardware for timer | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-14 21:39 | 2020-09-30 19:32 |  |  |  |  | 0 | 0
8 | Spike a Timer mockup | Open | Alex | Buddylgreen | Sam Forest | SamForest | No | No |  | 2020-09-14 21:40 | 2020-10-21 19:17 |  |  | 3 | In progress | 0 | 54000
9 | Ceremony Cadence 1 | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-21 22:01 | 2020-10-19 00:44 |  |  |  |  | 0 | 48600
10 | Create Definition of Done | Open | Vincent Krenz | krenzva |  |  | No | No |  | 2020-09-30 04:40 | 2020-10-19 05:00 |  |  |  |  | 0 | 1800
11 | Setup Common Development enviroment | Closed | Alex | Buddylgreen | Blake Masbruch | masbruchba | No | No |  | 2020-09-30 19:05 | 2020-10-12 22:31 | 2020-10-12 22:31 |  | 5 |  | 0 | 58800
12 | Setup Git Repository | Closed | Alex | Buddylgreen | Sam Forest | SamForest | No | No |  | 2020-09-30 19:10 | 2020-10-12 21:58 | 2020-10-12 21:58 |  | 2 |  | 0 | 3600
13 | Create timer setup screen | Open | Alex | Buddylgreen | Lucas | laroccol | No | No |  | 2020-09-30 19:17 | 2020-10-19 03:47 |  |  | 3 | In progress | 0 | 28800
14 | Create Timer Discovery | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-30 19:22 | 2020-10-05 22:32 |  |  | 5 | Ready To Work | 0 | 0
15 | Create Dataflow diagrams for timer | Open | Alex | Buddylgreen | Alex | Buddylgreen | No | No |  | 2020-09-30 19:26 | 2020-10-05 22:17 |  |  | 3 | In progress | 0 | 7200
16 | Negotiate with timer for configurations | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-30 19:33 | 2020-10-05 22:32 |  |  | 5 | Ready To Work | 0 | 0
17 | Create Logs / debug console page | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-30 19:38 | 2020-10-05 22:32 |  |  | 5 | Ready To Work | 0 | 0
18 | Ceremony Cadence 2 | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-10-08 | 2020-10-21 20:39 |  |  |  |  | 0 | 147600
19 | RethinkDB Streaming | Open | Alex | Buddylgreen | Blake Masbruch | masbruchba | No | No |  | 2020-10-12 22:13 | 2020-10-21 20:40 |  |  | 2 | In progress | 0 | 21600
20 | Process Improvement | Open | Vincent Krenz | krenzva |  |  | No | No |  | 2020-10-19 03:40 | 2020-10-19 05:00 |  |  | 3 |  | 0 | 10800
21 | Ceremony Cadence 3 | Open | Vincent Krenz | krenzva |  |  | No | No |  | 2020-10-19 22:36 | 2020-10-21 22:03 |  |  |  |  | 0 | 7200
36