## Sprint Report
| Cadence Report |  |  | Retrospective Presentation link
https://docs.google.com/presentation/d/1RBDKgBppNH0LCh4OKUocIOQGY-Doc8wSk4dwXFZVLuw/edit#slide=id.gb8e4d257dd_0_227
Project Name: | Drone Link | Cadence# | 2
Team Name: |  | Start: | End:
TEAM MEMBERS | Alex | 2021-01-03 | 2021-01-26
Lucas
Sam
Vincent
Blake
# of story points created at beginning of cadence | # of story points added throughout cadence | Total Story Points | # of story points completed (velocity)
31 | 5 | 36 | 28
| Cadence | Expected | Velocity
| 1 | 36 | 12
| 2 | 36 | 28
| Issues | % | Hours
Vincent | 5 | 17.86 | 19.5
Alex | 0 | 0 | 20
Blake | 13 | 46.43 | 28
Lucas | 5 | 17.86 | 17.5
Sam | 5 | 17.86 | 15
Impediments
Impediment | Reported On | Resolved On | Resolution
Retrospective
What went well in this cadence?
We were able to communicate well and establish future goals
Lots of development work got done
We were able to establish an overall design for the front-end of our project
What did not go well in this cadence?
Midterm time management for project
Overloading work on one member
Blocked tasks holding back team members
What can we do differently to improve?
We can make sure that work is done more consistently and not pushed off.
Help each other with tasks and make sure the work is dsitributed evenly

## Calculations
Issue ID | Title | State | Author | Author Username | Assignee | Assignee Username | Confidential | Locked | Due Date | Created At (UTC) | Updated At (UTC) | Closed At (UTC) | Milestone | Weight | Labels | Time Estimate | Time Spent | Epic ID | Epic Title
7 | Research hardware for timer | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-09-14 21:39 | 2020-09-30 19:32 |  |  |  |  | 0 | 0
14 | Create Timer Discovery | Closed | Alex | Buddylgreen | Lucas | laroccol | No | No |  | 2020-09-30 19:22 | 2021-01-21 23:07 |  |  | 5 | In Review | 0 | 43200
16 | Negotiate with timer for configurations | Open | Alex | Buddylgreen | Lucas | laroccol | No | No |  | 2020-09-30 19:33 | 2021-01-14 23:53 |  |  | 5 | In progress | 0 | 27000
24 | Input/Store Pilot Data | Closed | Vincent Krenz | krenzva | Lucas | laroccol | No | No |  | 2020-12-01 22:21 | 2021-01-21 23:07 |  |  | 5 | In Review | 0 | 0
25 | Ceremony Q2C1 | Open | Vincent Krenz | krenzva |  |  | No | No |  | 2020-12-01 22:53 | 2021-01-26 20:02 |  |  |  | Ready To Work | 0 | 159300
26 | Race data in system with mocks | Closed | Alex | Buddylgreen | Blake Masbruch | masbruchba | No | No |  | 2020-12-03 20:58 | 2021-01-26 20:03 |  |  | 8 | In Review | 0 | 111600
27 | Race Management dashboard | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-12-03 20:58 | 2020-12-08 23:55 |  |  |  |  | 0 | 0
28 | Timer Firmware Design / Research | Open | Alex | Buddylgreen |  |  | No | No |  | 2020-12-03 20:59 | 2020-12-03 20:59 |  |  |  |  | 0 | 0
30 | Frequency Management | Open | Alex | Buddylgreen | Alex, Vincent Krenz, Sam Forest | Buddylgreen, krenzva, SamForest | No | No |  | 2020-12-03 21:00 | 2021-01-26 02:59 |  |  | 13 | In progress | 0 | 41400
32 | Landing Page Content | Open | Vincent Krenz | krenzva |  |  | No | No |  | 2021-01-07 23:27 | 2021-01-07 23:42 |  |  |  |  | 0 | 0
33 | Page Linking | Closed | Vincent Krenz | krenzva |  |  | No | No |  | 2021-01-07 23:27 | 2021-01-26 20:02 |  |  |  | In Review | 0 | 14400
35 | Race Statistics Calculations | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:31 | 2021-01-14 23:31 |  |  |  |  | 0 | 0
36 | Login portal | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:31 | 2021-01-14 23:31 |  |  |  |  | 0 | 0
37 | Fan Portal | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:31 | 2021-01-14 23:31 |  |  |  |  | 0 | 0
38 | Pilot Main Page | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:32 | 2021-01-14 23:32 |  |  |  |  | 0 | 0
39 | Head to Head Heat formation | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:34 | 2021-01-14 23:34 |  |  |  |  | 0 | 0
40 | Schedule Heats for a day | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:34 | 2021-01-14 23:34 |  |  |  |  | 0 | 0
41 | Calendar view for all heats in a day | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:35 | 2021-01-14 23:39 |  |  |  |  | 0 | 0
42 | Ability to add specific racers to specific heats | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:40 | 2021-01-26 20:02 |  |  | 5 | In Review | 0 | 18000
43 | Saving race stats to link to pilot | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:40 | 2021-01-21 23:19 |  |  | 3 | Ready To Work | 0 | 0
44 | Run singular lap | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:41 | 2021-01-21 23:19 |  |  | 5 | Ready To Work | 0 | 0
45 | Run multiple laps | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:41 | 2021-01-21 23:23 |  |  | 5 | Ready To Work | 0 | 0
46 | Run multiple pilots | Open | Alex | Buddylgreen |  |  | No | No |  | 2021-01-14 23:41 | 2021-01-21 23:25 |  |  | 3 | Ready To Work | 0 | 0
0